## Timeline Tool
Timeline Tool - Online Video Implementation
Service :
|  |  | Project Start Date: | 00/00/2022
| For further information please email virtualhealth@hse.ie |  | Approx Schedule End Date: (16 weeks) | 00/00/2022
WBS | Task | Project Status (Dropdown Below) | Assigned To | Start | Duration (Days)
1 | Engage and Plan
1.1 | Complete project brief |  | Joe Bloggs | 10.10.2020 | 3 | Not started
1.1.1 | Project brief manager sign off | Not started |  |  |  | In progress
1.2 | Identify and engage with key stakeholders - Complete Stakeholders tab below | In progress |  | 2022-02-14 | 3 | High Priority
1.3 | Set up working group – complete working group tab below | High Priority |  |  |  | Complete
1.3.1 | Organise weekly meetings with working group | Complete
1.3.2 | Complete working group tab below
1.4 | Include video as a standing item on agendas
1.5 | Identify Initial service area to begin with |  |  | 2022-02-07
1.6 | Assess scope and scale for video usage
1.7 | Seek shared learning - NTPT/simuliar service/NMPDU |  |  | 2022-02-07
1.8 | Review change management guide included in slide deck
1.8.1 | Identify a framework for gathering evidence
1.9 | Identify potential risks - complete the tab below
1.9.1 | Circulate implementation guide slide deck to all necessay stakeholders
1.10. | Stakeholder tab complete
1.11 | Status update meeting with key stakeholders and working group inc. progress to date
2 | Review Processes Checklist
2.1 | Review existing process
2.1.1 | Map existing process (NB - engage with necessary stakholders)
2.1.2 | Identify video opportunities within existing process
2.2 | Update templates/SOP/Leaflet/Poster
2.3 | Identify contingency plan if video fails | Complete |  | 2022-02-07
2.4 | Have you considered how to record patient consent
2.4.1 | Review National Consent Policy
2.4.2 | Agree a process in line with existing on how to record patient consent
2.5 | Define eligibility criteria for suitable patient - clinican led
2.6 | Identify how patients will be offered/request an online health appointment
2.7 | Agree what information is to be given to the patient with the appointment link - Link on HSE national website, patient support page is very helpful
3 | Where, What & How Checklist
3.1 | Identify the location where online appointments/video communication will take place
3.2 | Review hardware and equipment available |  |  | 2022-02-07
3.3 | Review hardware and equipment required |  |  | 2022-02-07
3.4 | Order hardware and equipment required
3.5 | Review types of Online Health Appointment and video communication your service will facilitate from process map
3.6 | Agree and select video tool/s of choice in line with video opportunities (e.g. Webex/AttendAnywhere/blueeye….)
3.7 | Request email set up for staff who fdont have email address (if applicable) | High Priority
3.8 | Apply for video tool licenses
3.9 | Communicate use of video and create awareness - Display poster/brochures/website/pullup stand
3.10. | Status update meeting with key stakeholders and working group inc. progress to date
4 | Training, Go Live & Sustainability
4.1 | Schedule initial group training (champions/super users) - small group or watch/read training material available (Train a trainer approach)
4.2 | Trial platform/s among peers as clinician/patient before using with patient
4.3 | Practice/Trial/Test
4.4 | Schedule presentation with all staff
4.5 | Schedule training with all relevant staff (Train a trainer)
4.6 | Champions/Super users to support all staff
4.7 | Go Live Group 1 - internal
4.8 | Review readness and confidence before going out to the patient
4.9 | Status update meeting with key stakeholders and working group inc. progress to date
4.10. | Practice/Trial/Test
4.11 | Go Live Group 2 - small patient cohort
4.12 | Evaluate and Lessons Learned
4.12.1 | Review evidence captured
4.13 | Schedule next group training
4.14 | Trial platform among peers as clinician/patient before use
4.15 | Practice/Trial/Test
4.16 | Go Live Group 3 - scale up
5 | Readiness Checklist
5.1 | Planning complete
5.2 | Processes amended
5.3 | Processes reviewed
5.4 | Appropriate Environment identified
5.5 | Technology review complete
5.6 | Training & testing complete
5.7 | Trialing complete
5.7.1 | Review evidence captured
5.8 | Implementation complete | Complete
6 | Sustainability and embedding
6.1 | Review 3 months/6 months/1 year
6.2 | Project Close
6.3 | Record Decisions | High Priority
6.3.1 | Analyse and share data evidence
6.4 | Communicate to Stakeholders | Not started
6.5 | Project Evaluation and Lessons Learned
6.6 | Review 6 month | In Progress
6.7 | Evaluation/Lessons learned Meeting
6.8 | Review 1 year
To add more data, Insert new rows ABOVE this one

## Working Group
Name | Title | Role

## Risks
Risk Assesment | [6 empty] | Risk Possibilities
Identified Risk | Category | Impact (Low-Med-high) | Probability | Mitigaton | Responsible Person | Status (Open/Closed) | Lack of commitment from working group
Resistence from stakeholders
|  | Low |  |  |  |  | Resistence to change
|  | High |  |  |  |  | Technology issues/ Site infrastructure
|  | High |  |  |  |  | Resource Risks – Lack of availability of staff for planning, training, and coordination
|  | Low |  |  |  |  | Organizational Risks - Senior Management Support
Medium

## IssueLog
Issue Log
Identified Issue | Issue Oveview | Impact (Low-Med-high) | Responsible Person | Actionee | Status (Open/Closed) | Resolution Notes
High
Medium
Low